## Implementation plan
AI Agent for PRP Database
Stages | Aim | Progress | Problems | Solutions
Stage I - Keyword Search and Retrieval | Build the first working version of the AI agent to search keywords from documents stored in a folder and retrieve matching results accurately. | Completed keyword search and keyword retrieval from the folder. The functionality is working fine now. Multiple code breakdowns were handled during development. Python module issues were also resolved. | Python modules were not working correctly. Some code blocks were broken. Multiple errors occurred during execution. Repeated debugging was required. | Reinstalled and updated the required Python modules. Rewrote broken code multiple times. Fixed dependency issues and improved code stability. Final keyword search and retrieval process is working successfully.
Stage 2 – Summarization and Clean Output Generation | Summarize the keyword search results and extract useful data from the documents. Produce a clean, structured, and complete output in the form of steps, summary, or readable insights. | Planning stage. Keyword results are already available from Stage 1 and will be used as input for summarization. | Need to ensure summary is accurate, complete, and easy to understand. Need to avoid missing important keyword-related content from documents. Need to handle large document data properly. | Add summarization logic using AI/NLP model. Convert retrieved keyword results into clear summaries. Generate structured output with headings, steps, key findings, and document references if needed. Validate the output for readability and completeness.
Stage 3 – Secured Shared Folder and Network Access | Provide secured access to the client shared folder where documents are stored. The Python code should be able to scan/read documents from the shared network folder manually after access is provided. The AI agent should only read and process the documents without modifying, deleting, renaming, or changing any files in the shared folder. | Planned. Manual shared folder access is required from the client system/network team. Once access is provided, the Python code will scan documents from the secured shared location and process the data. | Shared folder is located in the client system, so access may be restricted. Network permissions may block Python code from reading files. There is a risk of accidentally modifying or changing client documents if proper restrictions are not followed. Security and compliance must be maintained. | Request read-only access to the shared folder. Ensure the Python code only performs read operations. Do not allow write, update, delete, move, or rename actions on client documents. Use a separate output folder for generated results. Maintain access control, folder permissions, and audit logs if required. Validate that the code can scan documents without changing original files.
Stage 4 – Extras, Backup, Shared Access and Readability | Add supporting features such as backup, shared folder access, code organization, readability improvements, and future maintenance support. | Planned for final enhancement stage after summarization is completed. | Risk of code loss without backup. Shared folder access may need permission handling. Code may become difficult to maintain if not organized properly. | Create backup copies of working code. Store code in a shared folder . Add proper comments and documentation. Improve folder structure and naming conventions. Maintain a readable README file with setup steps, usage steps, and troubleshooting points

## Log of issues
Stage | Issues
1 | Python modules were not working correctly. Some code blocks were broken. Multiple errors occurred during execution. Repeated debugging was required.
The designed GUI was removed for code modifications
Data is being retrieved but displayed output has some un necessary data shown like context numbers from the document.